## Contributions
Group: | PG29 | Software Engineering & Project Semseter 2 2017
Student Id | Name | Week 3 |  | Week 4 |  | Week 5 |  | Week 6 |  | Week 7 |  | Week 8 |  | Week 9 |  | Week 10 |  | Week 11 |  | Week 12
|  | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome | Activity | Outcome
a1729507 | Huy Nguyen Phan | Assemble robot from lego part flow instruction in calalog | Working robot with sensors ready for developement | Prepare SRS section 4 system feature | Finish first draft of section 4 in SRS Draft | Revise SRS section 4 follow client review | Finish SRS section 4 + Add requirement priority + Add requirement dependency + Add requirement ID | Group meeting disucss about SPMP document | Contribute idea in brainstorming meeting | Start developing Auto Surveying mode for milestone 1 demo | Inital draft Zigzaging movement in auto mode Inital draft of track/path flowing | Auto surveying mode development | Finish Zigzaging movement Finish track/path following | Milestone 2 preparation and testing | Success demo all feature of milestone 2 | Revise SDD section 5 | Add context for all diagram in section 5 | Implement move to waypoint feature | Robot will automatically move to a point on map while avoid obstacle, NGZ and crater. | Finish all development stuff and integrate features | A stable application ready for demo.
|  | Research and setup lejos enviroment | Successful setup lejos on Intellij IDE | Research about ant build | Success build a simple sample console application with Ant command | Study how to use java-fx and lejos api | Start developement on robot UI | Prepare section 7 of SPMP draft | Finish first draft of SPMP section 7 - Work Plan | Revise section SPMP 7 | Add Work Breakdown structure diagram into section 7 of SPMP | SDD document draft - section 5 | Finish section 5 draft - Class, state, integration diagram | Create ant build for Lunar Rover project | Can build project with ant command | Write unit-test | create set of unit-test for automation mode | Implement detect and survey radiation area | Robot can auto survey radiation area until it found apollo and move back to landing site | Do video recoding demo in case the real demo can not happened | Video demo all features
|  | Team meeting take note | Team meeting minute |  |  | Code review and refactor | Re-organize project structure and refactor code follow coding standard | Research ultra sonic sensor | Implement robot detect obstacle with ultra sonic sensor |  |  |  |  | Enhance follow track in automation mode | Robot can flow track/path effectively | Implement avoid NGZ and Crater in Auto Surveying mode | Robot can avoid obstacle, crater, NGZ zone in automation mode | Create automation test | When start application without connect to the robot. Automation data test will load and user can use similation to test the application | Create demo map | A map demo with color as define by lecturer
a1692282 | Kin Leong Lee | Setup the connection between EV3 and PC | Cannot establish the wifa connection between Robot and computer | Study JavaFX and try to add more Functions on GUI | Added keyboard listener to software and provide keybard shorcut to control robot | SRS revised | Remove the unecssary diagrams and re-design GUI | Create tools bar and help menu for GUI | Successfully implement | Study JUnit test | Will implement it next week | Working on SDD document | Finsihed GUI section | Research ant build file and trying to create it on intellji | Fail, can only run on personal computer My group member can generate it using eclipse and test it without any issue | Prepating Testing review, practise it and record to youtube | Complete it on time | Preparing mystery presentation and practise it | Complete it on time | Review the SRS, SPMP and SDD documents. To ensure that the revision history table and the format is correct | The final release is ready
|  | Configure IDE and LeJOS | We choose Intellij. Installed to my computer without any issue. For Lejos installation, I needs to install it twice. Finally, the Lejos is running on robot successfully | SRS preparation - Research on EV3 communication protocols | Finished the externel interface for SRS documents | Learning navigation class in Java | Fail to implement it. Consulting my group mamber and work with him. We implement it now | Working on SPMP | Finished the work organsition and configuration management | Revised SPMP | Fixed some formatting errors on SPMP | Create some test case on JUnit test | Successfully implement without any issue | Re-design the button image with team member | Successfullt implement | Modified SDD and SRS documents based on the newest version of GUI design | Completed | Perform the acceptance tests with group members and record the result, and outline a testing report | Compete it on time. The testing report is not a final version since our software manager want to continue the testing | Prepare the final presentation, make a ppt slides for testing review and practise it | Will perform rehersial with group members before Final Presentation day.
|  |  |  | Working manual control, implement some sensor function for testing the sensor functionalities with team member | Successfully implement | [6 empty] | Revised the help menu in GUI | Successfully revised | Draft some test cases | Discuss with team member and make a list of
a1711830 | Xiaoshan Chen | Build bricks | the robot prototype is formed | insert pictures Latex in SRS | can be inserted pictures into latex | formatting the requirements | revised the format according to the requirement. | SRS review | complete | Revised SPMP | Fixed some formatting errors on SPMP | Working on SDD document | Finsihed scope and constrants section | Re-design the button image with team member | Successfullt implement | help the group member to do the test review | complete | Preparing mystery presentation and practise it | Complete it on time | complete the user manual | the format is not good but fix finally
|  | Configure IDE and LeJOS | Installed IDE to my computer. The Lejos is running on robot successfully | Collecting constraints and features of robot prototype | present to the client for the next client meeting | learning navigation class in java | failed to implement the navigation class in java since the library is out of date | working on SPMP | finished the work of introduction and updated references | Study JUnit test | ready for implement the test case | Create some test cases on JUnit test | Successfully implement without any issue | Create some test cases on JUnit test | Successfully implement without any issue | Modified SDD and SRS documents based on the newest version of GUI design | Completed | Create some test cases on JUnit test for test manager | Complete it on time | re-design the map legend | update the color and shape of the representation on the map
|  |  |  | try control the robot manuallt, implement some sensor function for testing the sensor functionalities | Successfully implement |  |  |  |  | study gui design that group member design | ready for demo for the client meeting | design GUI | implement map legend | [6 empty] | Prepare the final presentation, make a ppt slides for process model | ready to present for the final presentation
|  | Review Client Specifications | Brainstorm several possible system architectures for the robot system | [8 empty] | present the Gui design to the client | complete
a1162759 | Ben Winding | Configure IDE | Helped install IntelliJ ide to all group members computers | Manual Control Research | Implement a prototype manual controlled version of the robot for the client demonstration | Add Map To JavaFX UI | Add initial version of map to GUI, displaying dot as robot location | SPMP Documentation Control | Add section on the standards by which the group will control documentation and implement changes | Implement Multithreaded Architecture | After research and design on how multithreaded programs work in Java, a simple implementation was achieved | SDD Document | Added detailed component decomposition | Movement Service | Implement movement service, a simpler api to be used by the automatec survey logic. | Map details added | Added better visualisations for map objects | Map Tests | Added tests to prove the accuracy of the map layer factory | Finalisation of documents | Finalise SDD for release, double check other documentation to ensure quality
|  | Research lejos api | Discovered several Lejos Api's that could be used for the system | Structure GitHub Repository | Create folder structure for the repository | Implement Navigator Class | Try to implement navigator class in robot system. Which allows the robot to be sent to a specific coordinate. | Robot Sensors implementation | Initial Version of sensors created. Detecting colours, naively. Determined limitations of the remote communication. | SDD architecture concepts | Created a architectural diagram for the system, using multiple stateless threads and a state repository. | GUI scaling | Implemented scaling on the GUI. Thumwheel scales the image | Sensor Service | Simplify access to the sensors state by using the state repository. All parts of the system have read only access to the sensor state | Map panning | Implemented ability to Pan the map in the GUI | NGZ detection | Implemented feature in which the robot can tell if it is in a bounded NGZ or not | Integration testing | Test robot with a series of integration tests with an example map
|  | Review Client Specifications | Brainstorm several possible system architectures for the robot system |  |  |  |  | Logging update | Implemented better logging to the console and to the GUI text output |  |  | Research Statemachines | Try to implement a statemachine to control the state of the robot and it's behaviour. Much harder than expected |  |  | SDD Review | Carry out SDD review video. Very cringey
a1162490 | Sean Hennessy | LeJOS research | Familiarised with leJOS and Java language | Research javaFX | keep up to date with other members work on project | Revise SRS section | Completed suggestion imporvements by tutor | SPMP document | Risk Mangement Section of SPMP complete | Research possible ways of map import/export | decide on JAXB library to create map objects/xml objects | Create working xml import/export function | created working function for basic map import/export | Map import/export tests | create some basic tests and validations | Create XML import validation method | complete | Updated import to match new NGZ/obstacle detection | complete
|  | IDE Configuration | Setup IDE on multiple computers | Study GitHub | Familiarise Github functions adn best practices | additional leJos class research | familiarise self with lejos classes to be used in robot | Additonal JavaFX research | familiarise with classes used to create map for future use in map object creation | SPMP improvements | added sections as suggested by feedback | SDD document | Added data / database design and diagram to SDD | continue details on map import representation | map visual representation closer to resembling actual map |  |  | Mystery presentation | complete | prepare for final presentation
|  |  |  | Srs Section completion | complete non-functional requirements |  |  |  |  | Study JUnit | Get ready for writing tests for xml import/export | Finish risk managemetn review | completed | [6 empty] | format and add sections to testing report | complete